## Phase 1
HCR Workqueue | Estimate |  | Dev Completion | QA Completion
In House | 5 |  | 100% | 100%
Discharge | 5 |  | 100% | 100%
Completed | 5 |  | 100% | 100%
|  |  | 100% | 100%
Page level filtering |  |  | 100% | 100%
Hospital group | 5 |  | 100% | 100%
hospital facility |  |  | 100% | 100%
Hospital |  |  | 100% | 100%
Visit status detail |  |  | 100% | 100%
Column level filtering | 8 |  | 100% | 100%
Column level sorting | 3 |  | 100% | 100%
Default filtering to assigned user | 8 |  | 100% | 100%
(Prioritization) | 5 |  | 100% | 100%
Grid Configuration based on user | 1 |  | 100% | 100%
Self-Assignment | 5 |  | 100% | 100%
Manager Assignment | 8 |  | 100% | 100%
New Referral Indicator (Visit) | 3 |  | 100% | 100%
Total: | 61 | Three sprints, 6 weeks to complete | 100% | 100%
|  |  | 100% | 100%
Intake Verification (Registration) |  |  | 100% | 20%
Patient Demographics | 8 |  | 100% | 20%
Visit Info | 8 |  | 100% | 20%
Ins info | 8 |  | 100% | 20%
Data Pre-Population | 5 |  | 100% | 20%
Data Verification | 8 |  | 100% | 20%
Prompting/Scripting | 8 |  | 100% | 20%
Recommended Input Fields | 5 |  | 100% | 20%
Read Only Person ID | 1 |  | 100% | 20%
Data formatting | 5 |  | 100% | 20%
Total: | 56 | Three sprints, 6 weeks to complete | 100% | 20%
Screening Portion - Eligibility |  |  |  | 0%
Dynamic Screening questions | 20 |  | 80% | 0%
eligibility Determination | 20 |  | 80% | 0%
Screening/Eligibility Summary Report | 20 |  | 80% | 0%
Recommended Programs | 60 | Three sprints, 6 weeks to complete | 80% | 0%
HCR Available Override Programs |  |  | 80% | 0%
Form Relationship Linkage(SC) |  |  | 0% | 0%
PACE Integration (POE API) |  |  | 10% | 0&